## Sheet1
PROJECT COMPLETION DATE | 2022-08-08
SPRINT | MVP | STORY | STATUS | STORY POINTS | POINTS CAPACITY | POINTS AVAILABLE | ASSIGNED TO | START DATE | FINISH DATE | DURATION IN DAYS | SPRINT LENGTH
Sprint 1 |  |  |  | 30 | 120 | 10 |  | 2022-07-25 | 2022-08-01 |  | 1 WEEK
Sprint 1 | Yes | "Home" page: Lawn Buddy overview | Complete | 1 |  |  | Gasser | 2022-07-25 | 2022-07-26 | 1
Sprint 1 | Yes | "Home" page: call-to-action button | Complete | 1 |  |  | Gasser | 2022-07-26 | 2022-07-27 | 1
Sprint 1 | Yes | "Home" page: how Lawn Buddy works | Complete | 1 |  |  | Gasser | 2022-07-27 | 2022-07-28 | 1
Sprint 1 | No | "Home" page: roadmap | Complete | 2 |  |  | Gasser | 2022-07-28 | 2022-08-01 | 4
Sprint 1 | Yes | "About Us" page: Lawn Buddy mission and culture | Complete | 1 |  |  | Hamnah | 2022-07-25 | 2022-07-26 | 1
Sprint 1 | Yes | "About Us" page: the team | Complete | 1 |  |  | Hamnah | 2022-07-25 | 2022-07-26 | 1
Sprint 1 | No | "About Us" page: advisors | Complete | 1 |  |  | Hamnah | 2022-07-26 | 2022-07-27 | 1
Sprint 1 | No | "About Us" page: partners | Complete | 1 |  |  | Hamnah | 2022-07-27 | 2022-07-28 | 1
Sprint 1 | No | "Blog" page: #1, concepts from the Lean Startup | Complete | 2 |  |  | Enaas | 2022-07-25 | 2022-07-26 | 1
Sprint 1 | No | "Blog" page: #2, object detection technology | Complete | 3 |  |  | Enaas | 2022-07-26 | 2022-07-27 | 1
Sprint 1 | No | "Blog" page: #3, additional technology | Complete | 3 |  |  | Enaas | 2022-07-27 | 2022-07-28 | 1
Sprint 1 | No | "Blog" page: #4, plugin | Complete | 3 |  |  | Enaas | 2022-07-28 | 2022-08-01 | 4
Sprint 1 | Yes | "Business Plan" page: marketing plan | Complete | 4 |  |  | Hamnah | 2022-07-28 | 2022-07-29 | 1
Sprint 1 | Yes | "Business Plan" page: product/service | Complete | 2 |  |  | Hamnah | 2022-07-29 | 2022-07-30 | 1
Sprint 1 | Yes | "Business Plan" page: operations | Complete | 4 |  |  | Hamnah | 2022-07-30 | 2022-08-01 | 2
Sprint 2 |  |  |  | 29 | 100 | 2 |  | 2022-08-01 | 2022-08-08 |  | 1 WEEK
Sprint 2 | Yes | "Support" page: FAQ | Complete | 2 |  |  | Gasser | 2022-08-01 | 2022-08-03 | 2
Sprint 2 | Yes | "Support" page: terms and conditions | Complete | 1 |  |  | Gasser | 2022-08-03 | 2022-08-05 | 2
Sprint 2 | Yes | "Support" page: privacy policy | Complete | 1 |  |  | Gasser | 2022-08-06 | 2022-08-08 | 2
Sprint 2 | No | "Career Opportunities" page: jobs available | Complete | 3 |  |  | Hamnah | 2022-08-01 | 2022-08-03 | 2
Sprint 2 | No | "Career Opportunities" page: benefits | Complete | 3 |  |  | Hamnah | 2022-08-03 | 2022-08-05 | 2
Sprint 2 | Yes | "Business Plan" page: financials | Complete | 4 |  |  | Hamnah | 2022-08-06 | 2022-08-08 | 2
Sprint 2 | Yes | "E-commerce" page: e-commerce app/plugin | Complete | 5 |  |  | Enaas | 2022-08-01 | 2022-08-03 | 2
Sprint 2 | Yes | "E-commerce" page: cart page | Complete | 5 |  |  | Enaas | 2022-08-03 | 2022-08-05 | 2
Sprint 2 | Yes | "E-commerce" page: checkout page | Complete | 5 |  |  | Enaas | 2022-08-06 | 2022-08-08 | 2
Backlog |  |  |  | 26
Backlog | No | Customer confirmation page | Not Started | 1
Backlog | No | Customer confirmation email | Not Started | 3
Backlog | No | Setup payment merchant service | Not Started | 4
Backlog | No | Setup database | Not Started | 5
Backlog | No | Profile/account page | Not Started | 2
Backlog | No | “About” Page: Testimonials | Not Started | 2
Backlog | No | "Blog” Page: News | Not Started | 1
Backlog | No | “Blog” Page: Gallery Page | Not Started | 2
Backlog | No | "Blog” Page: Case Studies/client page | Not Started | 2
Backlog | No | Promos & Specials | Not Started | 4
Formulas:
DURATION IN DAYS = DATEDIF([START DATE], [FINISH DATE], "YD")